## Sheet1
Risk_Title | Inherent_Severity | Inherent_Likelihood | Residual_Severity | Residual_Likelihood | Ownership | Status | Value_Stream | Cause | Effect | Impact | Mitigation | Contingency | Headline
Document Processing Gap | 3 | 3 | 3 | 3 | Adam | Needs Plan | Logged in | There isn’t a document management solution slated for initial SF release. | This compromises 3D credit because we use uploaded documents and categorize them so we can send the appropriate response interventions. | Not only will the inability to send response interventions hurt removal efficacy, but we have also testified in court that our current policy is to stop subsequent creditor interventions anytime we are apprised that a consumer has received documentary information that we requested. |  |  | Inability to Process Documents Breaks 3D Credit
Customer Life | 1 | 3 | 1 | 2 | Adam | Mitigated | Credit Repair | Direct care customers typically stay 8 months less than our target | Modeled assumptions of the financial plan get missed | Pressure on LTV | Have reporting that tightly monitors and understands customer life with early predictive models | Develop tailored Re-engagment campaigns folded into a customer experience communications plan | Customers Need To Stay Members for 20 Months
Subscription Cost | 2 | 2 | 1 | 1 | Adam | Mitigated | Logged in | We have a belief that subscription fees above $10 are more highly scrutinized by consumers | Difficulty to acquire clients | Pressure to LTV | Minimize subscription costs and clearly outline the value to the consumer | Price test in 2021 to find the optimal price points for volume and profitability | Consumers May Be Sensitive to Fees Above $10
Build IT Efficacy | 2 | 2 | 1 | 1 | Adam | Mitigated | Credit Repair | Anecdotal use of Credit Pop (Level Credit, a.k.a., RentTrack) didn't make a difference in a team member's score | Consumers don't see score improvement results from Build IT | Consumers don't see value from Build It feature set | Set expectations with messaging; set messaging to the right target audience | Develop abilities to fill the gaps and build credit with other strategies. | Build It Needs To Fullfil Member Expectations
Complex Value Props | 2 | 2 | 1 | 1 | Adam | Mitigated | Logged in | Complexity and vastness of product features | Difficult to create concise marketing messaging that will resonate with consumers and communicate value effectively | Confused users won't subscribe putting pressure on volume | Develop a compelling and informative "Launch Pad" experience and pithy product marketing descriptions to make the product components compelling and easy to understand | Develop tailored Re-engagment campaigns folded into a customer experience communications plan | We Need a Simple Hook for Marketing
Support Issues to FIs | 1 | 2 | 1 | 1 | Adam | Mitigated | Credit Repair | Chase reports customer service issues go directly to them versus us | Our relationship with FI brands is compromised | The value to the consumer goes down as we aren't able to offer our highest rewards; Business viability goes down as we forego FI revenue. | Clear messaging about a "General Program"; callout in HERO PLACEMENT | Tightly monitor and get feedback from FIs about any issues | We Cannot Increase Support Tickets To Our FIs
Reward IT Payout Delays | 1 | 3 | 1 | 2 | Adam | Mitigated | Logged in | Getting approval feedback from FI partners can sometimes take weeks to get | Subscribers have to wait with little transparency into the timelines or status of their rewards | Frustrated subscribers spike customer service tickets and churn at high rates | Set clear expectations that customers will get payment "after 1-2 billing cycles" by spotlighting the information clearly before they apply | Manage customer satisfaction through zen desk support tickets to clarify and track down payments | Payouts On Reward It Need To Be Swift
Bureau Relations | 3 | 3 | 3 | 3 | Adam | Mitigated | Credit Repair | Red tape around bureau agreements have unpredictable timelines | Development and QA will have delayed access to Bureau specific short-codes and environments | The schedule would be delayed and we miss Q1 delivery | Work with bureaus to create gap contracts that will allow us early access to components. Streamline negotiations, contract review, and legal approval processes. | Develop the architecture and user experience without dependencies on all three bureaus so that we can remove certain bureaus from production environments and launch with less than three bureaus | Slow Bureau Processes Put Pressure on Timelines
Outsource Quality | 3 | 2 | 2 | 1 | Adam | Mitigated | Logged in | Important modules are dependent on outsourced teams where communication is challenging | Communication is challenged or broken between internal and external teams | Quality of work | Manage resources tightly and with regular check-ins and demos | Bring failing components inhouse to manage more tightly | Nearshore Development Carries Challenges
Election 2020 | 1 | 3 | 1 | 2 | Adam | Mitigated | Credit Repair | Election in 2020 | Media costs up; attention down | Pressure on LTV and volume | Push to get the product into the public market by early summer, ramp up spend early, and ramp down as we get into competitive spending season. Thoroughly optimize the database marketing funnel and build a DB marketing war chest with a "wishlist" campaign during private betas | Reduce spend that does not meet our CPA targets | Media is Expensive in an Election Year
Truncated QA | 1 | 3 | 1 | 2 | Adam | Mitigated | Logged in | Truncated QA schedule | We aren't able to catch all development issues. | Production errors. | Put more on UAT to cover all look and feel QA responsibilities | Launch to limited audiences prior to a general launch | Compressed Timelines Leaves Less Time for QA
Reporting Blindspots | 2 | 2 | 1 | 1 | Adam | Mitigated | Credit Repair | Nightmarish paid media reporting |  |  | Build comprehensive reporting deck with all the criteria needed to effectively manage the marketing spend | Set the standards to pass out of beta testing and don't allow a product in the market that cannot pass our minimum standards. | We Need to Close Gaps in Media Reporting
Mobile Usability | 1 | 2 | 1 | 1 | Adam | Mitigated | Logged in | Rollouts of the http://creditrepair.com hybrid app showed bugs and errors because UI was better optimized for mobile web versus mobile apps | Poor user experiences in mobile apps | Frustrated subscribers spike customer service tickets and churn at high rates | Thoroughly vet systems with end-to-end testing, end user testing with private betas (Friends & Family 50 and Ambassador 250 prior to a general launch. | Push clients to the web interface as the primary means to engage | User Experiences Need to Be Steller on All Devices
Disparate Environments | 1 | 3 | 1 | 2 | Adam | Mitigated | Credit Repair | Environments not matching |  |  | Thoroughly vet systems with end-to-end testing, end user testing with private betas (Friends & Family 50 and Ambassador 250 prior to a general launch. | Set the standards to pass out of beta testing and don't allow a product in the market that cannot pass our minimum standards. | We Need to Vet Breaking Points in Our Systems
FI Feedback Delays | 3 | 3 | 2 | 2 | Adam | Mitigated | Logged in | We don't always hear from FIs in a timely manner that a subscriber was approved for credit. | Subscribers don't get their money | Frustrated subscribers spike customer service tickets and churn at high rates | Set clear expectations that customers will get payment "after 1-2 billing cycles" by spotlighting the information clearly before they apply | Manage customer satisfaction through zen desk support tickets to clarify and track down payments | FIs Tend to Give Delayed Feedback on Payouts
Resource Crashing | 2 | 3 | 2 | 2 | Adam | Mitigated | Credit Repair | CCPA, PCI, SFDC 2020 priorities | Resources will have to jump onto other projects to address fires and issues | Resource scarcity pushing back timelines | Block out key resources through beta testing and until launch | Have strategic discussions with executive team members to prioritized against the company vision and most important needs of the organization. | Resources Spread Thin Across Multiple Initiatives
System Disunity | 3 | 3 | 2 | 2 | Adam | Mitigated | Logged in | Various disparate systems that need to communicate and transfer information to each other — what is being sent won't be what is expected and get an error | Customer records where customer accounts aren't recognized (can't log in) or customers don't get reward it money or | Customers can't access or use products as designed | Thoroughly vet systems with end-to-end testing, end user testing with private betas (Friends & Family 50 and Ambassador 250 prior to a general launch. | Set the standards to pass out of beta testing and don't allow a product in the market that cannot pass our minimum standards. | We Need to Vet Breaking Points in Our Systems
Frenemy Partners | 3 | 1 | 2 | 1 | Adam | Mitigated | Credit Repair | We have major partners (Experian, & Level Credit) who also have B2C products in the space | Partners may seek to drop us after launch | The product will have gaps in feature sets, we won't be able to fulfill our promises to consumers, and we'll lose customers while having difficulty attracting new ones | Establish strong, mutually beneficial business agreements with the key strategic partners and make it difficult for them to sever ties. | Develop abilities to fill the gaps and build credit with other strategies. Limit dependencies on Experian and form a narrative around 2 bureau reports. | Service Partners Have Competing B2C Products
Resource Crashing | 2 | 3 | 2 | 2 | Adam | Mitigated | Logged in | CCPA, PCI, SFDC 2020 priorities | Resources will have to jump onto other projects to address fires and issues | Resource scarcity pushing back timelines | Block out key resources through beta testing and until launch | Have strategic discussions with executive team members to prioritized against the company vision and most important needs of the organization. | Resources Spread Thin Across Multiple Initiatives
Something New | 3 | 3 | 2 | 2 | Adam | Mitigated | Credit Repair | Various disparate systems that need to communicate and transfer information to each other — what is being sent won't be what is expected and get an error | Customer records where customer accounts aren't recognized (can't log in) or customers don't get reward it money or | Customers can't access or use products as designed | Thoroughly vet systems with end-to-end testing, end user testing with private betas (Friends & Family 50 and Ambassador 250 prior to a general launch. | Set the standards to pass out of beta testing and don't allow a product in the market that cannot pass our minimum standards. | We Need to Vet Breaking Points in Our Systems
Something Very New | 3 | 1 | 2 | 1 | Adam | Mitigated | Logged in | We have major partners (Experian, & Level Credit) who also have B2C products in the space | Partners may seek to drop us after launch | The product will have gaps in feature sets, we won't be able to fulfill our promises to consumers, and we'll lose customers while having difficulty attracting new ones | Establish strong, mutually beneficial business agreements with the key strategic partners and make it difficult for them to sever ties. | Develop abilities to fill the gaps and build credit with other strategies. Limit dependencies on Experian and form a narrative around 2 bureau reports. | Service Partners Have Competing B2C Products
More | 1 | 3 | 1 | 2 | Adam | Mitigated | Credit Repair | Environments not matching |  |  | Thoroughly vet systems with end-to-end testing, end user testing with private betas (Friends & Family 50 and Ambassador 250 prior to a general launch. | Set the standards to pass out of beta testing and don't allow a product in the market that cannot pass our minimum standards. | We Need to Vet Breaking Points in Our Systems
More More | 3 | 3 | 2 | 2 | Adam | Mitigated | Logged in | We don't always hear from FIs in a timely manner that a subscriber was approved for credit. | Subscribers don't get their money | Frustrated subscribers spike customer service tickets and churn at high rates | Set clear expectations that customers will get payment "after 1-2 billing cycles" by spotlighting the information clearly before they apply | Manage customer satisfaction through zen desk support tickets to clarify and track down payments | FIs Tend to Give Delayed Feedback on Payouts
More More More | 2 | 3 | 2 | 2 | Adam | Mitigated | Credit Repair | CCPA, PCI, SFDC 2020 priorities | Resources will have to jump onto other projects to address fires and issues | Resource scarcity pushing back timelines | Block out key resources through beta testing and until launch | Have strategic discussions with executive team members to prioritized against the company vision and most important needs of the organization. | Resources Spread Thin Across Multiple Initiatives
More More More More | 3 | 3 | 2 | 2 | Adam | Mitigated | Logged in | Various disparate systems that need to communicate and transfer information to each other — what is being sent won't be what is expected and get an error | Customer records where customer accounts aren't recognized (can't log in) or customers don't get reward it money or | Customers can't access or use products as designed | Thoroughly vet systems with end-to-end testing, end user testing with private betas (Friends & Family 50 and Ambassador 250 prior to a general launch. | Set the standards to pass out of beta testing and don't allow a product in the market that cannot pass our minimum standards. | We Need to Vet Breaking Points in Our Systems
More More More More More | 3 | 1 | 2 | 1 | Adam | Mitigated | Credit Repair | We have major partners (Experian, & Level Credit) who also have B2C products in the space | Partners may seek to drop us after launch | The product will have gaps in feature sets, we won't be able to fulfill our promises to consumers, and we'll lose customers while having difficulty attracting new ones | Establish strong, mutually beneficial business agreements with the key strategic partners and make it difficult for them to sever ties. | Develop abilities to fill the gaps and build credit with other strategies. Limit dependencies on Experian and form a narrative around 2 bureau reports. | Service Partners Have Competing B2C Products